                                                                    October 30, 2024

Good afternoon 😊

          Next week we will have our GO TEAM meeting, and we will discuss our proposed dates for the Uniform Committee. The proposed dates serve as a timeline for when we will have our data ready regarding *Frank Lebby Stanton’s* school wide uniform plan.

            December 9, 2024- Develop a stakeholder engagement plan to receive feedback on implementing a uniform and its components, if adopted. (Uniform committee will meet by this day and come up with the recommendations that will be presented to the stakeholders).

          February 04, 2025- Committee will recommend the optional school uniform components.

          March 07, 2025- The Committee will establish the student voting timeline and process.

 -The committee will determine the length of time the uniform will be in use before reconsideration.

           March 16, 2025- Committee will create a communication plan to inform the school community about the optional school uniform.

April 02, 2025 -Plan will be finalized

