**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: October 25th, 2019**

**THIS WEEK:**

* Foundations wall pours
* Storm Line B completed
* Lower level MEP’s continued
* Waterproofing at retaining wall
* Retaining wall backfill started

** **

** **

**NEXT WEEK – October 28 thru November 1:**

* Continue underslab ME
* Start slab prep at kitchen area

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
	+ Paid to date amount $1,469,778.75
* GMP#2 $28,686,295.00
	+ Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**