**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: October 4th, 2019**

**THIS WEEK:**

* Foundations wall pours
* Storm line install continued
* Upper Level detention pond install
* Waterproofing of foundation wall

** **

** **

**NEXT WEEK – October 7 thru October 11:**

* Foundation wall
* Storm line install
* Cutting of NE parking lot grade

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
	+ Paid to date amount $646,892.85
* GMP#2 $28,686,295.00
	+ Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**