**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: July 26th, 2019**

**THIS WEEK:**

* Level Construction to walk site looking at tires that need removed.
* Site Crew continued pond
* COA watershed is installing new 8” water line off of Hollowell with no cost to this project.
* Tree crew started cutting down trees
* LDP obtained at noon on 7/24.
* Haul off of trees began

A large green field with trees in the background

Description automatically generated A train traveling down a dirt road

Description automatically generated

A close up of a tree

Description automatically generated

**NEXT WEEK – July 29 thru August 2:**

* Building demo crew to start next Tuesday 7/30.
* Clear and grub crew to restart on Monday 7/29 to clean up site for demo crew to get started on slabs and footings
* Install web cam

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $0.00
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 17, 2020
* YMCA-ELC - September 14, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**