**Project: Woodson Park Academy & YMCA-ELC**

**Week Ending: September 13th, 2019**

**THIS WEEK:**

* Foundation wall crew mobilized
* Grading ongoing
* Storm line install ongoing
* Installed lower detention pond

A group of people walking down a dirt road

Description automatically generated A picture containing sky, ground, outdoor, tree

Description automatically generated

**A field of grass with trees in the background

Description automatically generated A close up of a desert area

Description automatically generated**

**NEXT WEEK – September 15 thru September 20:**

* Foundations
* Temp power
* Grading

**PAYMENT STATUS:**

* Gmp#1 $3,703,488.00
  + Paid to date amount $646,892.85
* GMP#2 $28,686,295.00
  + Paid to date amount $0.00

**SCHEDULED DATE OF SUBSTANTIAL COMPLETION**

* WPA – September 28, 2020
* YMCA-ELC - September 16, 2020

**PREPARED BY:**

* **Matt Dauber, Carroll Daniel Construction Co.**