|  |  |
| --- | --- |
| **Prepared For:** | Atlanta Public Schools |
| **Prepared By:** | Tyler Cade |

|  |  |
| --- | --- |
|  |  |
| Vapor Barrier Installed  | Rebar Turn Down Install |
|  |  |
|  |  |
|  |  |
|  |  |
|  |
|  |  |
| Slab On Grade Pour | Slab Rebar Placement  |
|  |
|  |  |

**Last Week’s Activities:**

* Completed temporary utilities
* Continued MEP slab rough in
* Continued plumbing slab inspections
* Started footing excavations
* Started footing inspections
* Started footing concrete pours
* Started slab on grade prep

**This Week’s Activities:**

* Continued MEP slab rough in
* Continued plumbing slab inspections
* Continued footing excavations
* Continued footing inspections
* Continued footing concrete pours
* Continued slab on grade prep
* Started slab inspections
* Started slab on grade concrete pours

**Next Week’s Activities:**

* Continue MEP slab rough in
* Continue plumbing slab inspections
* Continue footing excavations
* Continue footing inspections
* Continue footing concrete pours
* Continue slab on grade prep
* Continue slab inspections
* Continue slab on grade concrete pours
* Start CMU block installation

|  |  |
| --- | --- |
| **Contract & Billings****Contract**Current Contract Value**Billings**Date Last Billing SubmittedTotal Billed to Date (Including Retainage)Date of Last PaymentAmount Paid to DateAmount Open Receivables (Not Including Retainage)Percent Billed to Date | $1,519,1625/10/2022$153,410.50N/A$0$138,069.4511%  |