## Slide 1
Benteen
Elementary School
Weekly Construction Progress Report Week 06/19/2023-06/23/2023

## Slide 2: Current Activities 06/19/2023-06/23/2023
Fire Alarm Testing and Troubleshooting – Ongoing
Owner / Architect / Engineer Punch walk
Move-in Classroom Furniture - Ongoing
Electrical Final Inspection - Completed
Air Handling Units Install - Ongoing
Install Fencing – Outside Air Units
Install Kitchen Equipment
Wax stage – Area A
Upcoming Activities 06/26/23-06/30/23
Install River rock gravel around ground HVAC Units
Mechanical and Plumbing Final Inspections
Rooftop HVAC start-up
Paint Gas Line
Wax Gymnasium’s Stage
Classroom Furniture currently moving in

## Slide 3: Progress Photos
Install Air Handling Unit in the Gym
New Classroom furniture delivery
New Classroom Furniture Setup Prep
Install Fencing for Outside Air Units
Installation of Kitchen Equipment
Floor Protection for Furniture Installation

## Slide 4
Project Schedule
Schedule Status: On Schedule
Project Financials
Construction GMP: $9,989,727.77
Progress Billed to Date: $7,734,405.60
Budget Status: Within GMP